## Bug Overview
SKYBOOK ¦ BUG REPORTS
28 defects • Jira project SKYB • Source: Jira CSV export
Bug ID | Bug Summary | Priority | Severity | Jira Status | Related Story | Created
SKYB-30 | Same origin and destination are allowed in flight search | Medium | High | To Do | SKYB-4 | 09/Sep/26 6:19 PM
SKYB-31 | Return date earlier than departure date is allowed | Medium | High | To Do | SKYB-4 | 09/Sep/26 6:21 PM
SKYB-32 | Past departure and return dates are allowed | Medium | High | To Do | SKYB-4 | 09/Sep/26 6:22 PM
SKYB-33 | Flight search is allowed with zero adult passengers | Medium | High | To Do | SKYB-4 | 09/Sep/26 6:22 PM
SKYB-34 | Adults passenger count can be set to zero | Medium | High | To Do | SKYB-5 | 09/Sep/26 6:23 PM
SKYB-35 | Infant passenger count can exceed adult passenger count | Medium | High | To Do | SKYB-5 | 09/Sep/26 6:23 PM
SKYB-36 | Flight results are not sorted correctly by price from low to high | Medium | Medium | To Do | SKYB-7 | 09/Sep/26 6:24 PM
SKYB-37 | Nonstop only filter displays flights with stops | Medium | Medium | To Do | SKYB-6 | 09/Sep/26 6:25 PM
SKYB-38 | Turning off the Nonstop only filter does not restore the full flight list | Medium | Medium | To Do | SKYB-6 | 09/Sep/26 6:26 PM
SKYB-39 | Invalid email address without a valid TLD is accepted | Medium | Medium | To Do | SKYB-11 | 09/Sep/26 6:27 PM
SKYB-40 | Phone number with fewer than 7 digits is accepted | Medium | Medium | To Do | SKYB-11 | 09/Sep/26 6:28 PM
SKYB-41 | Future date of birth is accepted | Medium | Medium | To Do | SKYB-12 | 09/Sep/26 6:28 PM
SKYB-42 | Passenger type and date of birth mismatch is accepted | Medium | Medium | To Do | SKYB-12 | 09/Sep/26 6:28 PM
SKYB-43 | Passport expiry date before travel date is accepted | Medium | High | To Do | SKYB-13 | 09/Sep/26 6:29 PM
SKYB-44 | Two passengers can select the same seat | Medium | High | To Do | SKYB-15 | 09/Sep/26 6:29 PM
SKYB-45 | User can continue without assigning seats to all required passengers | Medium | High | To Do | SKYB-16 | 09/Sep/26 6:30 PM
SKYB-46 | Baggage quantity can be decreased below zero | Medium | Medium | To Do | SKYB-18 | 09/Sep/26 6:31 PM
SKYB-47 | Baggage quantity can exceed the allowed upper limit | Medium | Medium | To Do | SKYB-18 | 09/Sep/26 6:31 PM
SKYB-48 | SAVE10 promo code applies multiple discounts when applied repeatedly | Medium | High | To Do | SKYB-21 | 09/Sep/26 6:32 PM
SKYB-49 | Invalid promo code is accepted | Medium | Medium | To Do | SKYB-21 | 09/Sep/26 6:32 PM
SKYB-50 | Removing an applied promo code does not recalculate the total | Medium | Medium | To Do | SKYB-21 | 09/Sep/26 6:33 PM
SKYB-51 | Payment is accepted with required fields left blank | Medium | High | To Do | SKYB-23 | 09/Sep/26 6:33 PM
SKYB-52 | Expired card expiry date is accepted | Medium | High | To Do | SKYB-22 | 09/Sep/26 6:34 PM
SKYB-53 | CVV with fewer than 3 digits is accepted | Medium | High | To Do | SKYB-23 | 09/Sep/26 6:34 PM
SKYB-54 | Payment is allowed without accepting Terms & Conditions | Medium | High | To Do | SKYB-24 | 09/Sep/26 6:35 PM
SKYB-55 | Taxes and fees do not scale with passenger count | Medium | Medium | To Do | SKYB-25 | 09/Sep/26 6:36 PM
SKYB-56 | Starting a new booking does not clear previous passenger data | Medium | Medium | To Do | SKYB-29 | 09/Sep/26 6:36 PM
SKYB-57 | Child passenger fare is calculated using the adult fare | Medium | High | To Do | SKYB-22 | 10/Sep/26 4:38 PM

## Bug Details
SKYBOOK ¦ DEFECT DETAILS
Original reproduction steps, expected vs actual behavior, and source description
Bug ID | Bug Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Original Description
SKYB-30 | Same origin and destination are allowed in flight search | 1. Open the Search Flights page. 2. Select Halden Cross (HDX) as the origin. 3. Select Halden Cross (HDX) as the destination. 4. Click Search flights. | The system should prevent the user from selecting the same city as both origin and destination. | The system allowed Halden Cross (HDX) to be selected as both origin and destination and proceeded to the next page. | High | system allows the user to select the same city as both the origin and destination and proceed with the flight search. Steps to Reproduce: 1. Open the Search Flights page. 2. Select Halden Cross (HDX) as the origin. 3. Select Halden Cross (HDX) as the destination. 4. Click Search flights. Expected Result: The system should prevent the user from selecting the same city as both origin and destination. Actual Result: The system allowed Halden Cross (HDX) to be selected as both origin and destination and proceeded to the next page. {{Severity: High}}
SKYB-31 | Return date earlier than departure date is allowed | # Open the Search Flights page. # Select Round trip. # Set the departure date to Sep 29. # Set the return date to Sep 27. # Click Search flights. | The system should prevent the return date from being earlier than the departure date. | The system allowed the return date to be earlier than the departure date and proceeded to the next page. | High | The system allows the user to select a return date earlier than the departure date and proceed with the flight search. Steps to Reproduce: # Open the Search Flights page. # Select Round trip. # Set the departure date to Sep 29. # Set the return date to Sep 27. # Click Search flights. Expected Result: The system should prevent the return date from being earlier than the departure date. Actual Result: The system allowed the return date to be earlier than the departure date and proceeded to the next page. Severity: High
SKYB-32 | Past departure and return dates are allowed | # Open the Search Flights page. # Select departure and return dates earlier than today. # Click Search flights. | The system should prevent the user from selecting departure and return dates earlier than today. | The system allowed departure and return dates earlier than today and proceeded to the next page. | High | The system allows the user to select departure and return dates earlier than today and proceed with the flight search. Steps to Reproduce: # Open the Search Flights page. # Select departure and return dates earlier than today. # Click Search flights. Expected Result: The system should prevent the user from selecting departure and return dates earlier than today. Actual Result: The system allowed departure and return dates earlier than today and proceeded to the next page. Severity: High
SKYB-33 | Flight search is allowed with zero adult passengers | # Open the Search Flights page. # Set Adults to 0. # Set Children to 0. # Set Infants to 0. # Click Search flights. | The system should block the flight search unless at least one adult passenger is included. | The system allowed the search with 0 adults and proceeded to the next page. | High | The system allows the user to search for flights without including at least one adult passenger. Steps to Reproduce: # Open the Search Flights page. # Set Adults to 0. # Set Children to 0. # Set Infants to 0. # Click Search flights. Expected Result: The system should block the flight search unless at least one adult passenger is included. Actual Result: The system allowed the search with 0 adults and proceeded to the next page. Severity: High
SKYB-34 | Adults passenger count can be set to zero | # Open the Search Flights page. # Set Adults to 0. # Set Children to 0. # Set Infants to 0. # Click Search flights. | The number of adults should not be less than 1. | The system allowed 0 adults and proceeded to the next page. | High | The system allows the number of adult passengers to be set to 0 and proceeds with the flight search. Steps to Reproduce: # Open the Search Flights page. # Set Adults to 0. # Set Children to 0. # Set Infants to 0. # Click Search flights. Expected Result: The number of adults should not be less than 1. Actual Result: The system allowed 0 adults and proceeded to the next page. Severity: High
SKYB-35 | Infant passenger count can exceed adult passenger count | # Open the Search Flights page. # Set Adults to 1. # Set Children to 1. # Set Infants to 3. # Click Search flights. | The system should prevent the number of infants from exceeding the number of adults. | The system allowed 3 infants with only 1 adult and proceeded. | High | The system allows the number of infants to exceed the number of adults. Steps to Reproduce: # Open the Search Flights page. # Set Adults to 1. # Set Children to 1. # Set Infants to 3. # Click Search flights. Expected Result: The system should prevent the number of infants from exceeding the number of adults. Actual Result: The system allowed 3 infants with only 1 adult and proceeded. Severity: High
SKYB-36 | Flight results are not sorted correctly by price from low to high | # Open the flight search results page. # Select Price as the sorting option. # Review the order of the displayed flight prices. | Flight results should be sorted numerically by price from lowest to highest. | Results were displayed in the following price order: $1,328, $1,810, $1,845, $3,292, $3,405, $424. | Medium | The system does not sort flight results correctly by price from low to high. Steps to Reproduce: # Open the flight search results page. # Select Price as the sorting option. # Review the order of the displayed flight prices. Expected Result: Flight results should be sorted numerically by price from lowest to highest. Actual Result: Results were displayed in the following price order: $1,328, $1,810, $1,845, $3,292, $3,405, $424. Severity: Medium
SKYB-37 | Nonstop only filter displays flights with stops | # Open the flight search results page. # Enable the Nonstop only filter. # Review the displayed flight results. | Only flights with zero stops should be displayed. | The Nonstop only filter still displayed 1-stop flights, including VJ 205 and NL 111. | Medium | The Nonstop only filter displays flights that have stops. Steps to Reproduce: # Open the flight search results page. # Enable the Nonstop only filter. # Review the displayed flight results. Expected Result: Only flights with zero stops should be displayed. Actual Result: The Nonstop only filter still displayed 1-stop flights, including VJ 205 and NL 111. Severity: Medium
SKYB-38 | Turning off the Nonstop only filter does not restore the full flight list | # Open the flight search results page. # Enable the Nonstop only filter. # Review the displayed flights. # Turn off the Nonstop only filter. # Review the flight list again. | Turning off the Nonstop only filter should restore the full flight list for the current sort. | Turning the Nonstop only filter off did not change the displayed flight list. | Medium | The flight list does not change after turning off the Nonstop only filter. Steps to Reproduce: # Open the flight search results page. # Enable the Nonstop only filter. # Review the displayed flights. # Turn off the Nonstop only filter. # Review the flight list again. Expected Result: Turning off the Nonstop only filter should restore the full flight list for the current sort. Actual Result: Turning the Nonstop only filter off did not change the displayed flight list. Severity: Medium
SKYB-39 | Invalid email address without a valid TLD is accepted | # Open the Passenger Details page. # Enter test0022@gmail in the email field. # Complete the remaining required passenger details. # Continue to the next step. | The system should reject the invalid email address and display a validation message. | The system accepted the invalid email address test0022@gmail. | Medium | The system accepts an invalid email address that does not contain a valid top-level domain. Steps to Reproduce: # Open the Passenger Details page. # Enter test0022@gmail in the email field. # Complete the remaining required passenger details. # Continue to the next step. Expected Result: The system should reject the invalid email address and display a validation message. Actual Result: The system accepted the invalid email address test0022@gmail. Severity: Medium
SKYB-40 | Phone number with fewer than 7 digits is accepted | # Open the Passenger Details page. # Enter 07871 in the phone number field. # Complete the remaining required passenger details. # Continue to the next step. | The system should reject a phone number with fewer than 7 digits. | The system accepted the phone number 07871. | Medium | The system accepts a phone number with fewer than 7 digits. Steps to Reproduce: # Open the Passenger Details page. # Enter 07871 in the phone number field. # Complete the remaining required passenger details. # Continue to the next step. Expected Result: The system should reject a phone number with fewer than 7 digits. Actual Result: The system accepted the phone number 07871. Severity: Medium
SKYB-41 | Future date of birth is accepted | # Open the Passenger Details page. # Enter 11/12/2026 in the Date of Birth field. # Complete the remaining required passenger details. # Continue to the next step. | The system should not allow a future date of birth. | The system accepted the future date of birth 11/12/2026. | Medium | The system accepts a future date of birth for a passenger. Steps to Reproduce: # Open the Passenger Details page. # Enter 11/12/2026 in the Date of Birth field. # Complete the remaining required passenger details. # Continue to the next step. Expected Result: The system should not allow a future date of birth. Actual Result: The system accepted the future date of birth 11/12/2026. Severity: Medium
SKYB-42 | Passenger type and date of birth mismatch is accepted | # Open the Passenger Details page. # Select Adult as the passenger type. # Enter 06/15/2017 in the Date of Birth field. # Complete the remaining required passenger details. # Continue to the next step. | The system should flag the mismatch between the passenger type and the date of birth. | The system accepted an Adult passenger with date of birth 06/15/2017 without flagging the mismatch. | Medium | The system accepts a passenger as an Adult even when the entered date of birth does not match the Adult passenger age range. Steps to Reproduce: # Open the Passenger Details page. # Select Adult as the passenger type. # Enter 06/15/2017 in the Date of Birth field. # Complete the remaining required passenger details. # Continue to the next step. Expected Result: The system should flag the mismatch between the passenger type and the date of birth. Actual Result: The system accepted an Adult passenger with date of birth 06/15/2017 without flagging the mismatch. Severity: Medium
SKYB-43 | Passport expiry date before travel date is accepted | # Open the Passenger Details page. # Enter the travel dates Sep 29 – Oct 5, 2026. # Enter Sep 20, 2026 as the passport expiry date. # Complete the remaining required passenger details. # Continue to the next step. | The system should block the passenger from continuing because the passport expires before the travel dates and display a clear validation message. | The system accepted passport expiry Sep 20, 2026 for travel Sep 29 – Oct 5, 2026. | High | The system accepts a passport expiry date that is before the passenger's travel dates. Steps to Reproduce: # Open the Passenger Details page. # Enter the travel dates Sep 29 – Oct 5, 2026. # Enter Sep 20, 2026 as the passport expiry date. # Complete the remaining required passenger details. # Continue to the next step. Expected Result: The system should block the passenger from continuing because the passport expires before the travel dates and display a clear validation message. Actual Result: The system accepted passport expiry Sep 20, 2026 for travel Sep 29 – Oct 5, 2026. Severity: High
SKYB-44 | Two passengers can select the same seat | # Open the Seat Selection page for a booking with two passengers. # Select seat 4E for Passenger 1. # Select seat 4E for Passenger 2. | The system should prevent two passengers in the same booking from selecting the same seat. | Passenger 2 was able to select the same seat 4E already selected by Passenger 1. | High | The system allows two passengers in the same booking to select the same seat. Steps to Reproduce: # Open the Seat Selection page for a booking with two passengers. # Select seat 4E for Passenger 1. # Select seat 4E for Passenger 2. Expected Result: The system should prevent two passengers in the same booking from selecting the same seat. Actual Result: Passenger 2 was able to select the same seat 4E already selected by Passenger 1. Severity: High
SKYB-45 | User can continue without assigning seats to all required passengers | # Open the Seat Selection page for a booking with 2 adults. # Assign a seat to Passenger 1 only. # Leave Passenger 2 without a seat. # Verify the seat counter shows 1/2 seated. # Click Continue. | The system should prevent the user from continuing until all seat-holding passengers have assigned seats. | The system allowed continuing with only 1 of 2 seat-holding passengers seated. | High | The system allows the user to continue when not all seat-holding passengers have been assigned a seat. Steps to Reproduce: # Open the Seat Selection page for a booking with 2 adults. # Assign a seat to Passenger 1 only. # Leave Passenger 2 without a seat. # Verify the seat counter shows 1/2 seated. # Click Continue. Expected Result: The system should prevent the user from continuing until all seat-holding passengers have assigned seats. Actual Result: The system allowed continuing with only 1 of 2 seat-holding passengers seated. Severity: High
SKYB-46 | Baggage quantity can be decreased below zero | # Open the Extras page. # Locate the extra checked baggage quantity. # Decrease the baggage quantity below zero. | The baggage quantity should not be less than 0. | The baggage quantity could be decreased below zero to -4. | Medium | The system allows the extra baggage quantity to be decreased below zero. Steps to Reproduce: # Open the Extras page. # Locate the extra checked baggage quantity. # Decrease the baggage quantity below zero. Expected Result: The baggage quantity should not be less than 0. Actual Result: The baggage quantity could be decreased below zero to -4. Severity: Medium
SKYB-47 | Baggage quantity can exceed the allowed upper limit | # Open the Extras page. # Locate the extra checked baggage quantity. # Increase the baggage quantity above 10. | The baggage quantity should have a sane upper limit, such as 10 per passenger. | The baggage quantity could be increased to 20. | Medium | The system allows the extra baggage quantity to exceed the allowed upper limit. Steps to Reproduce: # Open the Extras page. # Locate the extra checked baggage quantity. # Increase the baggage quantity above 10. Expected Result: The baggage quantity should have a sane upper limit, such as 10 per passenger. Actual Result: The baggage quantity could be increased to 20. Severity: Medium
SKYB-48 | SAVE10 promo code applies multiple discounts when applied repeatedly | # Open the Extras & Promo Codes page. # Enter SAVE10 in the promo code field. # Click Apply. # Check the applied discount. # Click Apply again. # Check the discount again. | The valid promo code should apply the discount exactly once, regardless of repeated Apply actions. | SAVE10 initially applied -$118, but applying it again changed the discount to -$825. | High | The system applies the SAVE10 promo code more than once when the Apply button is clicked repeatedly. Steps to Reproduce: # Open the Extras & Promo Codes page. # Enter SAVE10 in the promo code field. # Click Apply. # Check the applied discount. # Click Apply again. # Check the discount again. Expected Result: The valid promo code should apply the discount exactly once, regardless of repeated Apply actions. Actual Result: SAVE10 initially applied -$118, but applying it again changed the discount to -$825. Severity: High
SKYB-49 | Invalid promo code is accepted | # Open the Extras & Promo Codes page. # Enter INVALID123 in the promo code field. # Click Apply. # Review the promo code message and price breakdown. | The system should reject the invalid promo code and display a clear error message. | The system displayed “Promo code applied!” for INVALID123 and added Promo INVALID123 -$0.00. | Medium | The system accepts an invalid promo code and displays a successful application message. Steps to Reproduce: # Open the Extras & Promo Codes page. # Enter INVALID123 in the promo code field. # Click Apply. # Review the promo code message and price breakdown. Expected Result: The system should reject the invalid promo code and display a clear error message. Actual Result: The system displayed “Promo code applied!” for INVALID123 and added Promo INVALID123 -$0.00. Severity: Medium
SKYB-50 | Removing an applied promo code does not recalculate the total | # Open the Extras & Promo Codes page. # Enter SAVE10 in the promo code field. # Click Apply. # Verify that the discount is applied. # Clear the promo code input. # Click Apply again. # Review the price breakdown. | Removing the applied promo code should immediately remove the discount and recalculate the total. | Clearing the promo code input and clicking Apply did not remove the applied discount. | Medium | The system does not remove the applied promo discount when the promo code is cleared. Steps to Reproduce: # Open the Extras & Promo Codes page. # Enter SAVE10 in the promo code field. # Click Apply. # Verify that the discount is applied. # Clear the promo code input. # Click Apply again. # Review the price breakdown. Expected Result: Removing the applied promo code should immediately remove the discount and recalculate the total. Actual Result: Clearing the promo code input and clicking Apply did not remove the applied discount. Severity: Medium
SKYB-51 | Payment is accepted with required fields left blank | # Open the Payment page. # Enter valid payment details in the required fields except Name on Card and Billing ZIP. # Leave Name on Card blank. # Leave Billing ZIP blank. # Complete the payment. | The system should block the payment when required payment fields are empty. | The system accepted payment with Name on Card and Billing ZIP left blank. | High | The system accepts payment even when required payment fields are left blank. Steps to Reproduce: # Open the Payment page. # Enter valid payment details in the required fields except Name on Card and Billing ZIP. # Leave Name on Card blank. # Leave Billing ZIP blank. # Complete the payment. Expected Result: The system should block the payment when required payment fields are empty. Actual Result: The system accepted payment with Name on Card and Billing ZIP left blank. Severity: High
SKYB-52 | Expired card expiry date is accepted | # Open the Payment page. # Enter valid card details. # Enter 01/25 in the Expiry field. # Complete the remaining required payment information. # Proceed with the payment. | The system should reject an expiry date that has already passed. | The system accepted the expired card expiry date 01/25. | High | The system accepts a payment card with an expired expiry date. Steps to Reproduce: # Open the Payment page. # Enter valid card details. # Enter 01/25 in the Expiry field. # Complete the remaining required payment information. # Proceed with the payment. Expected Result: The system should reject an expiry date that has already passed. Actual Result: The system accepted the expired card expiry date 01/25. Severity: High
SKYB-53 | CVV with fewer than 3 digits is accepted | # Open the Payment page. # Enter valid payment details. # Enter 15 in the CVV field. # Proceed with the payment. | The system should accept only a numeric CVV with exactly 3 or 4 digits. | The system accepted CVV 15. | High | The system accepts a CVV that does not meet the required length validation. Steps to Reproduce: # Open the Payment page. # Enter valid payment details. # Enter 15 in the CVV field. # Proceed with the payment. Expected Result: The system should accept only a numeric CVV with exactly 3 or 4 digits. Actual Result: The system accepted CVV 15. Severity: High
SKYB-54 | Payment is allowed without accepting Terms & Conditions | # Open the Payment page. # Enter valid payment details. # Leave the Terms & Conditions checkbox unchecked. # Click Pay now. | The system should block payment until the Terms & Conditions are accepted. | The system allowed Pay now without accepting the Terms & Conditions. | High | The system allows the user to complete the payment without accepting the Terms & Conditions. Steps to Reproduce: # Open the Payment page. # Enter valid payment details. # Leave the Terms & Conditions checkbox unchecked. # Click Pay now. Expected Result: The system should block payment until the Terms & Conditions are accepted. Actual Result: The system allowed Pay now without accepting the Terms & Conditions. Severity: High
SKYB-55 | Taxes and fees do not scale with passenger count | # Complete a booking search with 1 adult. # Check the Price breakdown. # Record the Fares, Taxes & fees, and Total. # Repeat the booking search with 2 adults. # Compare the Taxes & fees. | Taxes and fees should scale with the fare and passenger count and should not remain fixed. | Taxes & fees remained $45 for both 1 Adult and 2 Adults. | Medium | The system keeps the Taxes & fees amount fixed when the passenger count and fare change. Steps to Reproduce: # Complete a booking search with 1 adult. # Check the Price breakdown. # Record the Fares, Taxes & fees, and Total. # Repeat the booking search with 2 adults. # Compare the Taxes & fees. Expected Result: Taxes and fees should scale with the fare and passenger count and should not remain fixed. Actual Result: Taxes & fees remained $45 for both 1 Adult and 2 Adults. Severity: Medium
SKYB-56 | Starting a new booking does not clear previous passenger data | # Complete a booking. # Click Start a new booking. # Review the Search Flights page. # Check the passenger fields and previous booking selections. | Starting a new booking should clear all previous booking data, including flight, passengers, seats, extras, and payment information. | After clicking Start a new booking, the Search Flights page still showed 2 Adults, 0 Children, 1 Infant and 3 passengers selected from the previous booking. | Medium | The system retains passenger information from the previous booking after starting a new booking. Steps to Reproduce: # Complete a booking. # Click Start a new booking. # Review the Search Flights page. # Check the passenger fields and previous booking selections. Expected Result: Starting a new booking should clear all previous booking data, including flight, passengers, seats, extras, and payment information. Actual Result: After clicking Start a new booking, the Search Flights page still showed 2 Adults, 0 Children, 1 Infant and 3 passengers selected from the previous booking. Severity: Medium
SKYB-57 | Child passenger fare is calculated using the adult fare | # Complete a booking with 1 Adult only using the selected route, dates, and Economy cabin. # Record the fare. # Repeat the same booking with 1 Adult and 1 Child. # Review and compare the fare after adding the Child passenger. | The Child passenger should be charged the child fare exactly once and should not be calculated using the adult fare. | The system calculated the Child passenger fare using the adult fare instead of applying a separate child fare. | High | The system calculates the Child passenger fare using the adult fare instead of applying a separate child fare. Steps to Reproduce: # Complete a booking with 1 Adult only using the selected route, dates, and Economy cabin. # Record the fare. # Repeat the same booking with 1 Adult and 1 Child. # Review and compare the fare after adding the Child passenger. Expected Result: The Child passenger should be charged the child fare exactly once and should not be calculated using the adult fare. Actual Result: The system calculated the Child passenger fare using the adult fare instead of applying a separate child fare. Severity: High

## Project Summary
SKYBOOK ¦ QA DEFECT SUMMARY
Metric | Value | Jira Status | Count
Project | SkyBook – Flight Booking | To Do | 28
Jira Key | SKYB
Reported Bugs | 28
Test Cases | 48
Source | Jira CSV Export
|  | Severity (description) | Count
Severity is extracted from Jira descriptions when present. |  | High | 15
|  | Medium | 13
All 28 original defect descriptions are retained in the Bug Details sheet. Jira statuses and priorities are unchanged.